## Sheet1
NO | STLC PHASE | INPUT | ACTIVITIES | RESPONSIBILITY | OUTCOME
1 | Reqirement Analysis | Project Plan | Reviewing SRD/BRD/FRD | Business Analyst | Clear & Complete Finalized Requirements
|  |  | Interviewing stakeholders to gather additional information | Customers/Stake holders
|  |  | Identifying any missing or incomplete requirements | Test Manager/Lead
Tets Enginners
2 | Test Planning | Project Plan | Identify the Resources | Test Manager/Lead | Test Plan Document
| What to test , How to test & when to test? | Functional Requirement Document(FRD) | Team Formation | Test Engineers
Test Estimation
Preparation of Test Plan
Reviews on Test Plan
Test Plan Sign-off
3 | Test Designing/Development | Project Plan | Preparation of Test Scenarios | Test Lead | Test Cases Document
|  | Functional Requirement Document(FRD) | Preparation of Test Cases | Test Engineers | Traceability Matrix
|  | Test Plan | Reviews on Test Cases
|  | Design Docs /UI Specification | Traceability Matrix
|  | Use cases / Wireframes | Test Cases Sign-off
4 | Test Environment Setup & Execution | Functional Requirement Document(FRD) | Environment Setup Executing Test cases | Test Lead | Status/Test Reports
|  | Test Plan | Executing Test cases | Test Engineers | Defect Report
|  | Test Cases | Preparation of Test Report/Test Log
|  | Build from Development Team | Identifying Defects
Preparation of Defect Report
Reporting Defects to Developers
5 | Test Closure/Sign-Off | Test Reports | Analyzing Test Reports | Test Manager/Lead | Test Summary Reports
|  | Defect Reports | Analyzing Bug Reporting | Test Engineers
Evaluating Exit Criteria

## Sheet2
NO | STLC PHASE | REFERENCE DOCUMENTS | ACTIVITIES | RESPONSIBILITY | OUTCOME
1 | Reqirement Analysis | Project Plan | 1. Reviewing SRD/BRD/FRD 2. Interviewing stakeholders to gather additional information 3. Identifying any missing or incomplete requirements | Business Analyst Stake holders Test Manager Test Lead Test Engineers | Clear & Complete Finalized Requirements
2 | Test Planning | Project Plan Functional Requirement Document(FRD) | 1. Identify the Resources 2. Team Formation 3. Test Estimation 4. Preparation of Test Plan 5. Reviews on Test Plan 6. Test Plan Sign-off | Test Manager Test Lead Test Engineers | Test Plan Document
3 | Test Development | Project Plan Functional Requirement Document(FRD) Test Plan Design Docs /UI Specification Use cases / Wireframes | 1. Preparation of Test Scenarios 2. Preparation of Test Cases 3. Reviews on Test Cases 4. Traceability Matrix (RTM) 5. Test Cases Sign-off | Test Lead Test Engineers | Test Cases Document Traceability Matrix
4 | Test Environment Setup & Execution | Functional Requirement Document(FRD) Test Plan Test Cases Build from Development Team | 1. Environment Setup Executing Test cases 2. Executing Test cases 3. Preparation of Test Report/Test Log 4. Identifying Defects 5. Preparation of Defect Report 6. Reporting Defects to Developers | Test Lead Test Engineers | Status/Test Reports Defect Report
5 | Test Closure/Sign-Off | Test Reports Defect Reports | 1. Analyzing Test Reports 2. Analyzing Bug Reporting 3. Evaluating Exit Criteria | Test Manager Test Lead Test Engineers | Test Summary Reports